## Dashboard
Full Project |  |  | Choose Module | Specific Module
# | Data
Project Name |  | V1 |  | # | Total TC | Pass | Fail | Not Executed
Created By | Mohamed Elbadri |  |  | Cycle 1 | 0 | 0 | 0 | 0
Date |  |  |  | Cycle 2 | # | 0 | 0 | 0
Total TC | 26
PASS | 14
Fail | 12
Not Executed | 0

## V1
Verify (Suite) | [7 empty] | Cycle 1 |  |  | Cycle 2
ID | Test Scenario | Test Case | Precondition | Test Data | Test Steps | Expected | Actual | Status | Defect ID | Describtion | Status | Defect ID | Describtion
TC_IS_001 | Request a quotation | Validate Broker can Request a quotation with valid data | 1 - website opened 2 - broker loged in 3 - request page opened 4 - info avaliable | Breakdowncover - roadside Windscreenrepair - NO Number Of Accidents - 1 Registration Number - 2 Total Mileage - 100 Value - 110 Parking - public start - 1/1/2024 |  | message displayed that say "quotation requested successfully" and quatation number with premium amount displayed | As Expected | PASS |  |  | Not Executed
TC_IS_002 |  | Validate Broker can Request a quotation with no cover type |  |  |  | premium displayed and the amount is increased by 1% | message displayed Premium: £NaN | FAIL |  |  | Not Executed
TC_IS_003 |  | Validate Broker can Request a quotation with road cover type |  |  |  | premium displayed and the amount is increased by 2% | Wrong calc,message displayed Premium: £200 | FAIL |  |  | Not Executed
TC_IS_004 |  | Validate Broker can Request a quotation with at home cover type |  |  |  | premium displayed and the amount is increased by 3% | Wrong calc,message displayed Premium: £300 | FAIL |  |  | Not Executed
TC_IS_005 |  | Validate Broker can Request a quotation with european cover type |  |  |  | premium displayed and the amount is increased by 4% | Wrong calc,message displayed Premium: £400 | FAIL |  |  | Not Executed
TC_IS_006 |  | Validate Broker can Request a quotation with no windScreenRepair |  |  | Select from dropdown list | premium displayed and the amount is increased by 0 EURO |  | PASS |  |  | Not Executed
TC_IS_007 |  | Validate Broker can Request a quotation with windScreenRepair |  |  |  | premium displayed and the amount is increased by 30 EURO |  | PASS |  |  | Not Executed
TC_IS_008 |  | Validate Broker can Request a quotation with zero acciedents |  |  |  | premium displayed and the amount is decreased by 30% |  | PASS |  |  | Not Executed
TC_IS_009 |  | Validate Broker can Request a quotation with number of acciedents |  |  |  | premium displayed and the amount is not changed |  | PASS |  |  | Not Executed
TC_IS_010 |  | Validate Broker can Request a quotation with number of milage greater than 5001 |  |  |  | premium displayed and the amount is increased by 50 EURO |  | FAIL |  |  | Not Executed
TC_IS_011 |  | Validate Broker can Request a quotation with number of milage equal to 5001 |  |  |  | premium displayed and the amount is increased by 50 EURO |  | FAIL |  |  | Not Executed
TC_IS_012 |  | Validate Broker can Request a quotation with number of milage equal to 5000 |  |  |  | premium displayed and the amount is not changed |  | FAIL |  |  | Not Executed
TC_IS_013 |  | Validate Broker can Request a quotation with number of milage less than 5000 |  |  |  | premium displayed and the amount is not changed |  | FAIL |  |  | Not Executed
TC_IS_014 |  | Validate Broker can Request a quotation with estimate value greater than 100 |  |  |  | message displayed that say "quotation requested successfully" and quatation number with premium amount displayed |  | PASS |  |  | Not Executed
TC_IS_015 |  | Validate Broker can Request a quotation with estimate value equal to 100 |  |  |  | message displayed that say "quotation requested successfully" and quatation number with premium amount displayed |  | PASS |  |  | Not Executed
TC_IS_016 |  | Validate Broker can Request a quotation with estimate value equal to 99 |  |  |  | message displayed that say "not procesed" |  | PASS |  |  | Not Executed
TC_IS_017 |  | Validate Broker can Request a quotation with estimate value less than 99 |  |  |  | message displayed that say "not procesed" |  | PASS |  |  | Not Executed
TC_IS_018 |  | Validate Broker can Request a quotation with public parking |  |  |  | premium displayed and the amount is increased by 30 EURO |  | FAIL |  |  | Not Executed
TC_IS_019 |  | Validate Broker can Request a quotation with garage parking |  |  |  | premium displayed and the amount is not changed |  | PASS |  |  | Not Executed
TC_IS_020 |  | Validate Broker can view premium amount without saving |  |  |  | message displayed with the amount of the premium |  | PASS |  |  | Not Executed
TC_IS_021 | Retrieve quotation | Validate Broker can Retrieve quotation with valid data | 1 - website opened 2 - broker loged in 3 - retrive page opened 4 - info avaliable | number - 34025 |  | message displayed with the quotation info |  | PASS |  |  | Not Executed
TC_IS_022 |  | Validate Broker can Retrieve quotation with invalid data |  |  |  | message displayed that say" the qution number is wrong" |  | PASS |  |  | Not Executed
TC_IS_023 |  | Validate Broker can Retrieve quotation with his own data |  |  |  | message displayed with the quotation info |  | PASS |  |  | Not Executed
TC_IS_024 |  | Validate Broker can Retrieve quotation with not owned data |  |  |  | message displayed that say" the qution number is not found" |  | FAIL |  |  | Not Executed
TC_IS_025 | Edit Profile | Validate Broker can edit his profile | 1 - website opened 2 - broker loged in 3 - edit page opened 4 - info avaliable |  |  | message displayed that say" account info updated" |  | FAIL |  |  | Not Executed
TC_IS_026 | View Profile | Validate Broker can view his profile | 1 - website opened 2 - broker loged in 3 - view page opened |  |  | message displayed with the profile info |  | FAIL |  |  | Not Executed