## Dashboard
Total Bugs
# | Total Bugs | Open bugs | Closed bugs | Fixed bugs
Cycle 1 | 12 | 0 | 0 | 12

## Bugs
ID | Status | TC_ID | Version | Describtion | Steps | Expected | Actual | Priority | Severity
bug_1 | Fixed | TC_integration_001 | v1 | CONNECTION ERROR with the server | 1 - enter the userID 2 - click submit button 3 - enter all required fields 4 - click submit | message appears to the user that say the new customer is added successfully | Could not connect: Access denied for user 'root'@'localhost' (using password: NO) | Medium | Medium
bug_2 | Fixed | TC_integration_002 | v2 |  |  | message appears to the user that say theis email is used before, try with another email | Could not connect: Access denied for user 'root'@'localhost' (using password: NO) | Medium | Medium
bug_3 | Fixed | TC_integration_003 | v3 |  | 1 - enter the userID 2 - click submit button 3 - enter all required fields 4 - click submit | message appears that say "customer info is updated successfully" | Could not connect: Access denied for user 'root'@'localhost' (using password: NO) | Medium | Medium
bug_4 | Fixed | TC_integration_004 | v4 |  |  | the new data that previously edited should be updated successfully and appears in the right field | Could not connect: Access denied for user 'root'@'localhost' (using password: NO) | Medium | Medium
bug_5 | Fixed | TC_integration_005 | v5 |  | 1 - enter the userID 2 - click submit button | message appears to the user that say "the userID is wrong" | Could not connect: Access denied for user 'root'@'localhost' (using password: NO) | Medium | Medium
bug_6 | Fixed | TC_integration_006 | v6 |  | 1 - enter the userID 2 - click submit button 3 - enter all required fields 4 - click submit | message appears to the user that say "the data is not updated " | Could not connect: Access denied for user 'root'@'localhost' (using password: NO) | Medium | Medium
bug_7 | Fixed | TC_integration_007 | v7 |  | 1 - enter the userID 2 - click submit button | message appears to the user that say "the CUSTOMER DATA IS SUCCESSFULLY deleted " | Could not connect: Access denied for user 'root'@'localhost' (using password: NO) | Medium | Medium
bug_8 | Fixed | TC_integration_008 | v8 |  |  | message appears to the user that say "this customer id is not exist" | Could not connect: Access denied for user 'root'@'localhost' (using password: NO) | Medium | Medium
bug_9 | Fixed | TC_integration_009 | v9 |  |  |  | Could not connect: Access denied for user 'root'@'localhost' (using password: NO) | Medium | Medium
bug_10 | Fixed | TC_integration_010 | v10 |  | 1 - enter UserID 2 - choose the account type from the drop down list 3 - enter the deposite value 4 - click submit | message appears that say "account is created successfully" | Could not connect: Access denied for user 'root'@'localhost' (using password: NO) | Medium | Medium
bug_11 | Fixed | TC_integration_011 | v11 |  |  |  | Could not connect: Access denied for user 'root'@'localhost' (using password: NO) | Medium | Medium
bug_12 | Fixed | TC_integration_012 | v12 |  | 1 - enter the required fields 2 - click submit | mini statements is generated successfully and the user can see it | Could not connect: Access denied for user 'root'@'localhost' (using password: NO) | Medium | Medium